## How to use
Roofing Job Tracker
A free roofing job tracker spreadsheet: move jobs from lead to install to paid with value, stage, and crew notes for roofers, in Sheets and Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Move leads through to paid; Promised turns red when an estimate or install date slips.
3 | Insurance jobs: record the claim number and collect the deductible per your state's rules.
4 | Mark Stage as "Paid" when money arrives; the Summary tab splits price into collected and outstanding.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Squares | Insurance claim | Balance | Days open
2026-10-01 | Vance | Tear-off + architectural shingles | Materials ordered | Crew A | 2026-10-17 | 16800 | 5000 | 29 | TRV-2041188 | 11800 | 11
2026-10-05 | Kim | Storm repair + gutters | Signed | Crew B | 2026-10-22 | 6400 | 0 | 8 | SF-77120934 | 6400 | 7
2026-10-09 | Harbor HOA (bldg C) | Flat roof TPO | Estimate sent |  | 2026-10-18 | 38500 | 0 | 60 |  | 38500 | 3
2026-10-11 | Lee | Leak inspection | Inspection | Sales: Dana | 2026-10-14 | 0 | 0 | 0 |  | 0 | 1
2026-09-13 | Ortiz | Full replacement | Paid | Crew A | 2026-10-01 | 14200 | 14200 | 24 |  | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Paid")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (promised) | 0
By stage
Stage: Lead | 0
Stage: Inspection | 1
Stage: Estimate sent | 1
Stage: Signed | 1
Stage: Materials ordered | 1
Stage: Installed | 0
Stage: Paid | 1
Totals
Total price | 75900
Total deposit | 19200
Total balance | 56700
Collected | 14200
Outstanding | 61700