## How to use
Siding Job Tracker
A free job tracker for siding contractors: schedule jobs, assign crews, and track product and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Check the color and profile against the order when materials arrive; reorders take weeks.
3 | Promised turns red when a phase runs late.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Product / color | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-28 | Vance | Vinyl, premium, Harbor Gray | Install | Crew A | 2026-10-16 | 24800 | 8000 | 16800 | 14
2026-10-04 | Kim | Fiber cement, Arctic White | Materials ordered | Crew B | 2026-10-27 | 31500 | 10000 | 21500 | 8
2026-10-10 | Lee | Vinyl repair (storm) | Signed | Crew B | 2026-10-19 | 2400 | 0 | 2400 | 2
2026-09-08 | Ortiz | Vinyl, Pebblestone Clay | Paid | Crew A | 2026-10-03 | 19900 | 19900 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Paid")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 0
Stage: Signed | 1
Stage: Materials ordered | 1
Stage: Tear-off | 0
Stage: Install | 1
Stage: Trim and cleanup | 0
Stage: Paid | 1
Totals
Total price | 78600
Total deposit | 37900
Total balance | 40700