## How to use
Sign Job Tracker
A free sign job spreadsheet: track jobs from quote to install by type, stage, and due date with a workload view in Google Sheets and Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Promised dates turn red when passed and the sign is not Installed; permits are the usual hold-up.
3 | Get a signed proof before production; Balance shows what to collect at install.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Job | Stage | Designer | Promised | Price | Deposit | Sign type | Balance | Days open
2026-09-23 | Bloom Florist | Storefront panel and window vinyl | Production | Kara | 2026-10-16 | 2850 | 1425 | Panel | 1425 | 19
2026-09-29 | Northside Dental | Lit channel letters | Permit | Sam | 2026-11-03 | 9800 | 4900 | Channel letters | 4900 | 13
2026-10-07 | Lakeside 5K | Banners (6) and A-frames | Design proof | Kara | 2026-10-18 | 1240 | 620 | Banner | 620 | 5
2026-10-10 | City parks | Trail signs (12) | Deposit paid | Sam | 2026-11-10 | 4300 | 2150 | Post and panel | 2150 | 2
2026-09-13 | Brew Co | Vehicle wrap | Installed | Kara | 2026-10-04 | 3600 | 3600 | Vehicle graphics | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Installed")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (promised) | 0
By stage
Stage: Quoted | 0
Stage: Deposit paid | 1
Stage: Design proof | 1
Stage: Permit | 1
Stage: Production | 1
Stage: Install scheduled | 0
Stage: Installed | 1
Totals
Total price | 21790
Total deposit | 12695
Total balance | 9095