## How to use
Solar Install Pipeline
A free solar pipeline spreadsheet: track projects from sold to permit to install to PTO with system size and value, in Google Sheets and Excel.
Quick start
1 | Open the Projects tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Move each project through the stages and set the next milestone date; it turns red when missed.
3 | Days since sale turns amber after 90 days; PTO (permission to operate) is when the customer starts saving.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Projects
Customer | Sold date | System (kW) | Contract value | Stage | Next milestone by | PM | Days since sale | Price per watt
Kapoor | 2026-10-01 | 8.2 | 24640 | Design | 2026-10-16 | Lena | 11 | 3.0049
Ortiz | 2026-09-08 | 6.4 | 19200 | Permit submitted | 2026-10-23 | Lena | 34 | 3
Harbor Dental | 2026-08-14 | 24 | 61200 | Permit approved | 2026-10-11 | Marco | 59 | 2.55
Lee | 2026-07-30 | 7.6 | 22800 | Installed | 2026-10-18 | Marco | 74 | 3
Brennan | 2026-06-25 | 10.2 | 29600 | Inspection | 2026-10-07 | Lena | 109 | 2.902
Shah | 2026-05-26 | 9 | 26100 | PTO | 2026-09-23 | Marco |  | 2.9
Formulas:
Days since sale = IF([Customer]="","",IF(([Stage]="PTO"),"",(TODAY()-[Sold date])))

## Summary
Item | Value | Notes
Overview
Entries | 6
Overdue (next milestone by) | 2
By stage
Stage: Sold | 0
Stage: Site survey | 0
Stage: Design | 1
Stage: Permit submitted | 1
Stage: Permit approved | 1
Stage: Installed | 1
Stage: Inspection | 1
Stage: PTO | 1
Totals
Total contract value | 183540