## How to use
Stucco Job Tracker
A free job tracker for stucco contractors: move jobs through lath, scratch, brown, and finish coats with crew and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Allow cure time between coats; Promised is the target for the current coat and turns red when late.
3 | Mist-cure base coats in hot, dry weather to avoid cracking.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-29 | Kim | Two-story addition, 3-coat | Brown coat | Crew A | 2026-10-18 | 21400 | 7000 | 14400 | 13
2026-10-05 | Harbor Grill | Patch and color match, storefront | Lath | Crew B | 2026-10-19 | 3800 | 1200 | 2600 | 7
2026-10-10 | Lee | Garden wall finish | Estimate |  | 2026-10-20 | 2900 | 0 | 2900 | 2
2026-09-03 | Ortiz | Whole-house re-coat | Complete | Crew A | 2026-10-03 | 18600 | 18600 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 1
Stage: Lath | 1
Stage: Scratch coat | 0
Stage: Brown coat | 1
Stage: Finish coat | 0
Stage: Cleanup | 0
Stage: Complete | 1
Totals
Total price | 46700
Total deposit | 26800
Total balance | 19900