## How to use
Sunroom Build Tracker
A free build tracker for sunroom builders: track foundation, frame, and finish phases with crew and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Four-season rooms need foundation and energy-code inspections; Promised turns red when a phase slips.
3 | Collect progress payments at foundation, dry-in and completion.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Room type | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-03 | Holt | 14x16 four-season, gable roof | Glazing and roof | Crew A | 2026-10-19 | 48500 | 20000 | 28500 | 39
2026-09-23 | Sato | 12x12 three-season screen room | Foundation | Crew B | 2026-10-23 | 21800 | 8000 | 13800 | 19
2026-10-03 | Kline | Patio enclosure | Permit |  | 2026-11-07 | 16400 | 5000 | 11400 | 9
2026-07-15 | Parker | 16x20 four-season | Complete | Crew A | 2026-09-29 | 62000 | 62000 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Design | 0
Stage: Permit | 1
Stage: Foundation | 1
Stage: Framing / kit | 0
Stage: Glazing and roof | 1
Stage: Electrical and finish | 0
Stage: Final inspection | 0
Stage: Complete | 1
Totals
Total price | 148700
Total deposit | 95000
Total balance | 53700