## How to use
Surveying Project Invoice
A free invoice template for surveying firms: bill clients by job and phase with percent-complete and outstanding totals in Sheets or Excel.
Quick start
1 | Open the Phases tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Enter each phase's contract fee and its % complete; this invoice bills what's earned minus what you've already billed.
3 | Put reimbursables on their own line at 100% complete. The Summary tab totals the invoice.
4 | The Summary tab totals every line, applies your discount and tax rate (yellow cells), and shows the final total.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Phases
Phase | Phase fee | % complete | Previously billed | Amount this invoice
Boundary survey | 6500 | 100% | 6500 | 0
Topographic survey | 9800 | 100% | 4900 | 4900
Construction staking | 14500 | 40% | 2900 | 2900
As-built survey | 5200 | 0% | 0 | 0
Reimbursable expenses (recording, mileage) | 386 | 100% | 0 | 386

## Summary
Item | Value | Notes
Details
Invoice # | LS-2026-0419
Client | Meridian Civil Engineers
Job | Cedar Ridge subdivision – Phase 2
Invoice date | 2026-10-13
Due date | 2026-11-12
Totals
Subtotal | 8186
Tax rate | 0% | Your local sales tax rate, e.g. 0.0825 for 8.25%. Leave 0 if not taxable.
Discount | 0 | Flat discount in dollars.
Tax | 0
Total | 8186