## How to use
Tree Crew Schedule
A free tree crew schedule spreadsheet: assign crews and equipment by date with double-booking alerts and status for arborists, in Sheets and Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Equipment booked counts jobs needing the same machine that day; amber means two crews want it (like the bucket truck on day 2).
3 | Call 811 before stump grinding and confirm crane setup space and permits for removals near the street.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Date | Crew | Customer | Address | Work | Equipment | Est. hours | Contract price | Status | Equipment booked
2026-10-14 | Crew 1 | Holt | 31 Ivy Ln | Removal | Crane | 6 | 3800 | Scheduled | 1
2026-10-14 | Crew 2 | Ramos | 44 Ivy Ln | Pruning | Bucket truck | 4 | 950 | Scheduled | 1
2026-10-14 | Crew 3 | Sato | 7 Hilltop Ct | Stump grinding | Stump grinder | 2 | 425 | Scheduled | 1
2026-10-15 | Crew 1 | Brookside HOA | 900 Brook Rd | Pruning | Bucket truck | 8 | 2400 | Scheduled | 2
2026-10-15 | Crew 2 | Kline | 18 Elm St | Removal | Bucket truck | 5 | 1800 | Scheduled | 2
2026-10-12 | Crew 1 | Parker | 6 Ridge Way | Storm cleanup | Chipper only | 6 | 1600 | Complete | 1

## Summary
Item | Value | Notes
Overview
Entries | 6
By status
Status: Scheduled | 5
Status: In progress | 0
Status: Complete | 1
Status: Weather delay | 0
Totals
Total contract price | 10975
Total est. hours | 31