## How to use
Virtual Event Budget
A free virtual event budget spreadsheet: track platform, talent, and production costs with estimate-vs-actual and sponsorship offsets in Sheets and Excel.
Quick start
1 | Open the Budget tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Budget each line before contracts are signed and record actual cost as invoices arrive.
3 | Sponsorship and ticket income offset cost on the Totals tab.
4 | Enter Budget once, then update Actual as money goes out. Remaining turns red when a line is over budget.
5 | The Summary tab keeps running totals and counts. It updates as you add rows.
6 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget
Category | Line item | Budget | Actual | Notes | Remaining | % used
Platform | Event platform license (1 day, 1,000 attendees) | 4500 | 4500 | Includes registration | 0 | 100%
Talent | Keynote speaker fee | 8000 | 8000 |  | 0 | 100%
Talent | Moderator and MC | 1500 | 1750 | Added rehearsal | -250 | 116.7%
Production | Remote production crew (2 days) | 6200 | 6800 | Extra tech check day | -600 | 109.7%
Production | Speaker kits (mic, light) | 1200 | 960 | 8 kits | 240 | 80%
Marketing | Paid social | 2500 | 1900 |  | 600 | 76%
Swag | Attendee box (200) | 5000 | 0 | Not yet ordered | 5000 | 0%
Contingency | Reserve | 2000 | 0 |  | 2000 | 0%

## Totals
Item | Value | Notes
Income
Sponsorship income | 12000
Ticket income | 9000
Net
Total budget | 30900
Total actual | 23910
Net cost after income | 2910

## Summary
Item | Value | Notes
Overview
Entries | 8
Totals
Total budget | 30900
Total actual | 23910
Total remaining | 6990