## How to use
Waterproofing Job Tracker
A free job tracker for waterproofing contractors: schedule jobs, assign crews, and track scope and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Record transferable warranties for each job; buyers ask about them when the house sells.
3 | Promised turns red when a phase slips; call 811 before any exterior excavation.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-10-01 | Holt | Interior drain + sump, 120 lf | Membrane and drainage | Crew A | 2026-10-15 | 11400 | 4000 | 7400 | 11
2026-10-05 | Sato | Exterior membrane, north wall | Excavation / prep | Crew B | 2026-10-19 | 14800 | 5000 | 9800 | 7
2026-10-10 | Kline | Crack injection (3) | Signed | Crew A | 2026-10-18 | 1350 | 0 | 1350 | 2
2026-09-13 | Parker | Crawlspace encapsulation | Complete | Crew B | 2026-10-01 | 6900 | 6900 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Inspection | 0
Stage: Proposal | 0
Stage: Signed | 1
Stage: Excavation / prep | 1
Stage: Membrane and drainage | 1
Stage: Backfill and cleanup | 0
Stage: Complete | 1
Totals
Total price | 34450
Total deposit | 15900
Total balance | 18550