## How to use
Photographer Client Workflow
A free client workflow for wedding photographers: track each client from contract to delivery with deadline flags in Sheets or Excel.
Quick start
1 | Open the Clients tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Track each couple from inquiry to album; Gallery due turns red if editing runs past your contract window.
3 | Hold the date only after the contract is signed and the retainer paid.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Clients
Couple | Wedding date | Package | Contract signed | Retainer paid | Package price | Paid to date | Stage | Gallery due | Balance | Final payment due
Kim and Alex | 2026-11-02 | 10 hours + second shooter | Yes | Yes | 5200 | 2600 | Timeline set | 2026-12-14 | 2600 | 2026-10-03
Priya and Sam | 2026-12-12 | 8 hours | Yes | Yes | 4200 | 1400 | Engagement session | 2027-01-23 | 2800 | 2026-11-12
Ana and Ben | 2026-10-01 | 8 hours | Yes | Yes | 4200 | 4200 | Editing | 2026-11-12 | 0 | 2026-09-01
Leo and Mia | 2026-08-04 | 6 hours | Yes | Yes | 3400 | 3400 | Gallery delivered | 2026-09-15 | 0 | 2026-07-05
J. and R. | 2027-05-01 | Elopement | No | No | 1800 | 0 | Inquiry | 2027-06-12 | 1800 | 2027-04-01
Formulas:
Gallery due = IF([Couple]="","",([Wedding date]+'Studio'!$B3))
Final payment due = IF([Couple]="","",([Wedding date]-'Studio'!$B4))

## Studio
Item | Value | Notes
Policy
Delivery window (days) | 42 | Promised in your contract.
Final payment days before | 30
Workload
Galleries in editing | 1
Money
Balances due | 7200
Unsigned contracts | 1 | No date is held until signed and retainer paid.