## How to use
Well Drilling Job Tracker
A free job tracker for well drillers: schedule sites, assign crews and rigs, and track depth and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Bill drilling by the actual foot; Actual depth vs. Est. depth explains the final invoice.
3 | File the well log with your state after completion; water test results go to the owner.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Site / scope | Stage | Rig / crew | Promised | Price | Deposit | Est. depth (ft) | Actual depth (ft) | Balance | Days open
2026-10-01 | Hill farm | New domestic well | Drilling | Rig 1 / Ray | 2026-10-16 | 14800 | 4000 | 280 | 210 | 10800 | 11
2026-10-05 | Sato | Pump replacement | Pump install | Service truck / Lou | 2026-10-14 | 2900 | 0 | 0 | 0 | 2900 | 7
2026-10-08 | Kline | New well + pressure tank | Permit | Rig 1 / Ray | 2026-10-27 | 16200 | 4000 | 320 | 0 | 12200 | 4
2026-09-13 | Parker | New domestic well | Complete | Rig 2 / Dan | 2026-10-03 | 13900 | 13900 | 260 | 245 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Permit | 1
Stage: Drilling | 1
Stage: Casing and grout | 0
Stage: Pump install | 1
Stage: Water test | 0
Stage: Complete | 1
Totals
Total price | 47800
Total deposit | 21900
Total balance | 25900